Not started
In progress
Finished
Optional
V1 – limited access, pre-mainnet
Midas testing
with forking possibilities
(request estimation)
Public Tracer API + Plugin v1
With limited access
(Dmitriy Miroshnichenko)
1 day
Tracer-API Monitoring
(Ivan Loboda)
1d
Graph-dependent dApps testing:
- Questnbook
- Sobel
…?
Additionaly:
Estimate request rate produced by the Graph
Public Graph-node with limited access
(Dmitriy Miroshnichenko)
1 day
Debug loading tests Tracer API + plugin v1
(Ivan Loboda/Oleg Sukharev/Evgeniy Kurkovich)
1-3 days
Implement
load test cases
(Evgeniy Kurkovich)
4-5 days
V2 – full public access, mainnet
Plugin v2
Denis Avvakumov
5-7 days
Full public environment -
Tracer API + Graph-node
Questions to discuss:
- per-client request rate limits?
- authorization for graph deployment?
Integration testing
Tracer API + plugin v2
Ivan Loboda/Denis Avvakumov
1-2 days
Loading tests Tracer API + plugin v2
(Ivan Loboda/Oleg Sukharev/Evgeniy Kurkovich)
1 days
Kafka cluster deployment Dmitriy Miroshnichenko
1-2 days
Data filtration service for plugin v2
Ivan Loboda/Denis Kepeschuk
4-5 days